## Gantt Chart
DNP Project Name Here | [6 empty] | Updated: | 2019-03-22
Status | Stage | Task | Start | Duration (days) | End | Responsible Resource
Project Identification (NDNP810)
cpt |  | Start of Spring Term | 2019-01-28 | 1 | 2019-01-29 | Team
|  | Identify stakeholders/needs | 2019-01-29 | 10 | 2019-02-08 | MH
|  | Identify roles/responsibilities | 2019-02-08 | 20 | 2019-02-28
|  | Identify practice problem | 2019-01-28 | 40 | 2019-03-09
|  | Estimate resources | 2019-03-09 | 15 | 2019-03-24
|  | Identify scope/goals | 2019-01-28 | 20 | 2019-02-17
|  | Development project plans | 2019-01-29 | 20 | 2019-02-18
|  | MILESTONE: Submit project proposal | 2019-05-05 | 1 | 2019-05-06
|  | End of Spring Term | 2019-05-17 | 1 | 2019-05-18
Project Development (NDNP811)
|  | Start of Summer Term | 2019-06-03 | 1 | 2019-06-04
|  | Develop implemenation plans | 2019-06-03 | 25 | 2019-06-28
|  | Develop communication plan | 2019-06-03 | 20 | 2019-06-23
|  | Conduct risk analysis, contingency plans | 2019-07-03 | 20 | 2019-07-23
|  | MILESTONE: IRB Approval | 2019-07-23 | 1 | 2019-07-24
|  | End of Summer Term | 2019-07-26 | 1 | 2019-07-27
Project Implementation (NDNP812)
|  | Start of Fall Term | 2019-08-26 | 1 | 2019-08-27
|  | MILESTONE: Project go-live (implement) | 2019-08-26 | 15 | 2019-09-10
|  | Monitor tasks and progress | 2019-09-10 | 75 | 2019-11-24
|  | Communicate with stakeholders | 2019-08-26 | 80 | 2019-11-14
|  | Collect data | 2019-09-10 | 75 | 2019-11-24
|  | End of Fall Term | 2019-12-20 | 1 | 2019-12-21
Project Evaluation and Dissemination (NDNP813)
|  | Start of Spring Term | 2020-01-29 | 1 | 2020-01-30
|  | Analyze, synthesize & evaluate results | 2020-01-29 | 60 | 2020-03-29
|  | Document lessons learned | 2020-03-29 | 12 | 2020-04-10
|  | Plan corrective actions | 2020-04-10 | 15 | 2020-04-25
|  | MILESTONE: Submit manuscript | 2020-04-27 | 1 | 2020-04-28
|  | End of Spring Term | 2020-05-18 | 1 | 2020-05-19
Formulas:
End = [Start]+[Duration (days)]
Start = [End, row above]
Start = [Start, row above]
TODAY
< MOBALIZE
< ASSESS
< PLAN
< IMPLEMENT
< TRACK

## Instructions
Instructions for using UMSON Excel template for creating and managing your Gantt Chart
Overview: This spreadsheet is simply one table with an associated graph (the chart). All Excel formulas, and formatting will work. If you have no experience with Excel then you'll first need to take basic tutorials available from Microsoft online. Due to the extremely limited timeframe for your projects we encourage you to keep this schedule simple, and not invest a lot of time in elaborate formatting, sub tasking detail, etc. This spreadsheet is intended to be a SIMPLE and an easy substitute to MS Project or numerous other specialized tools available to manage project schedules. It has limitations of course. Some of these include the inability to create detailed reports such as PERT charts, or resource utilization, or the ability to automatically calculate and monitor your project's "critical path". If these or other limitations are a barrier to working on your project several tool alternatives are recommended in the QI Brief FAQ posted in Black Board.
I. Initially creating your project's Gantt Chart Starting with this template you'll first want to make it represent you project specifically. Please consider starting with the default tasks and durations until you've discussed the project in detail with some team members, sponsors, or champions.
1. Enter your Project Title in Cell A1. 2. Enter todays date in Cell K1. Update this date whenever you make substantial changes to your schedule
3. Format the Date Axis of the chart: Click on the Dates Axis to select the axis. Right-click and select Format Axis from the menu. You get the view shown here. Enter the data in the fomula to obtain the "Datevalue" necessary for the "Minimum" and "Maximum" bounds.
| Example Date >> | 2020-05-30
| Enter "Date" in formula >> | =DATEVALUE("05/30/2020")
43981
Type the resulting 5 digits into the Minimum Bounds. Repeat for your end date into the Maximum Bounds
You're welcome to use slightly different start or end dates for convience or appearance. You are also able to further adjust appearance by changing other options in the Format view.
II. Defining the task schedule Complete the table fields as described below.
Field Name | Instructions
Status | Free-form text. Suggest at least entering "CPT" where tasks are completed. Also helpful are "Underway", "Delayed". This (and other) columns can simply be "hidden" if not used.
Stage | Drag the appropriate "MAP-IT" QI Process Model stage to be adjacent to the related tasks.
Task | Enter/change the task description. It should start with an action verb, and it should be concise.
Start | Date the task is planned to start. It will be very common for several tasks to be sequential, so a simple formula here is very helpful to automate adjusting the schedule when some early task duration or timing gets delayed. See graphic below for example formula.
The above example forces the second Task to start immediately following the End of the previous task. It is also common to have the formula lock the Start Date to another task Start Date (e.g. =F2 in the above example). Or, you can lock it to another Start or End date with a delay or pre-start (e.g. =F2+10).
Duration (days) | The number of days the task is expected to take. This is the most likely length of time, NOT the best case or worst case.
End | This is the CALCULATED planned End Date, based on the Start Date and Duration. I.E. the End date equals the Start Date + duration days. See example below:
Note that it is highly recommended to NOT enter dates directly in the End Date cells as it will create errors in the Gantt Chart. If you have a specific End Date in mind you should adjust the Start Date and/or the Duration accordingly.
Responsible Resource | Enter the name or initials of the team member responsible for completing the task. Be certain that the named individual is aware of their task assignment!
III. Managing the Schedule
All your changes will happen to the table. You should not have to make any manual changes to the Gantt Chart. If you choose to hide table columns not used, you can select the chart and move it to the left. You can overlay any graphics over the chart to highlight important tasks or milestones, or note reasons for delays, etc. A sample note is provided, to be edited, copied, or deleted.
Inserting or Deleting Tasks | Highlight the Row#, right click, select Insert or Delete from menu
Copying or Backing up the tasks | Please keep back-up copies of your work. It is also best practice to mange version control. This can be done simply by naming the file to include the "Last Updated" date.
Creating a .ppt graphic | If a schedule graphic is needed for a presentation one can highlight the entire schedule, including the Gantt Chart, and copy n "paste special" as a picture into a powerpoint slide. The number of tasks will cause the graphic to be too small to read though. Tasks rows can be temporarily hidden to create an abreviated summary schedule.